# Memo: International Transfer Release – QA Position

To: Delivery Manager     From: QA Lead     Subject: Request to confirm "QA is green"     Go-live: in 3 working days

## 5.1 Recommendation

I can't confirm that QA is green. On today's evidence my recommendation is no-go, changing to go if the five conditions below are met by the Day 2, 12:00 checkpoint. The client decides whether to accept any residual risk; my responsibility is that they decide on accurate evidence.

Why not green today:

- A 68% pass rate means nothing until every failure is explained, and "probably flaky" is a guess, not a result.

- The FX integration, the part of this release that moves money, has had one round of happy-path testing.

- The two KYC criticals sit in the customer profile service that this journey also uses.

- UAT is half done and not signed off.

Conditions for go:

- Every regression failure classified as product defect, test defect or environment issue, none unexplained in the transfer, FX or profile paths. A "flaky" test must pass three consecutive runs, or be quarantined with its coverage checked manually.

- FX failure modes tested on staging: provider down or slow, stale rate, expired quote, rounding, rejected transfer, plus an end-to-end reconciliation of debits, credits and fees.

- KYC criticals assessed: the dev lead confirms in writing whether the root cause is in the shared profile service; if it is, the transfer steps that read the profile are re-tested.

- Client UAT signed off on the critical transfer journeys (the remaining scripts agreed with them).

- Rollback or feature-flag switch-off rehearsed, and alerts for failed or stuck transfers live in production.

If the conditions are not met, I will offer the client two alternatives: a later date, or a limited release behind a feature flag (e.g. a staff pilot). The trade-off I will put to them: a delay costs marketing credibility; a failed launch of a money-moving journey costs customer funds, regulator attention and trust in both of us, and is far harder to recover from.

## 5.2 Next 72 hours (priority order)

| # | When | Action | Owner |
| --- | --- | --- | --- |
| 1 | Day 1 AM | Triage every regression failure. The two experienced QAs take transfer, FX and profile failures; the two newer QAs pair with them. | QA Lead |
| 2 | Day 1 | FX failure-mode testing with an FX developer (condition 2). | QA + FX dev |
| 3 | Day 1 | KYC impact analysis with the dev lead (condition 3). | Dev Lead |
| 4 | Daily | 15-minute session with the client's UAT team: agree critical scripts, triage their defects the same day. | QA Lead |
| 5 | Day 2, 12:00 | Checkpoint: evidence against each condition; recommend go, limited release or delay. | QA Lead |
| 6 | Day 3 | Final regression and smoke test on the exact release-candidate build; rollback rehearsal. | QA team |

Capacity: about 12 person-days (5 triage and FX, 2 UAT support, 3 final regression, 2 reserve). If triage finds more than the reserve can absorb, I flag the date at the checkpoint, not on Day 3. New QAs pair, and the team keeps normal hours: tired testers miss defects.

Dropped: new automation, fixing flaky test code (quarantine now, fix later), cosmetic defects, out-of-scope regression, documentation polish.

## 5.3 Communication

Delivery manager (in writing, today): "I can't confirm green yet. Here is the status with evidence, the five conditions with owners and dates, and the Day 2 checkpoint." I will offer to join the client conversation.

Client (with the delivery manager, once the message is agreed): the business risk in plain language, what we are doing, the decision date, and the options with their consequences.

Can differ: level of detail (individual failures, team allocation), framing (actions and owners internally; business risk and options for the client) and vocabulary ("flaky" internally, "unverified results" for the client).

Must not differ: the facts (pass rate, open criticals, UAT status, FX gaps), the recommendation and its conditions, and who decides: the client accepts or rejects the residual risk. If pressed to report green against this evidence, I will escalate to the delivery head.

## 5.4 Changes for the next release

- Flaky-test policy: unexplained failures triaged within 24 hours, then fixed or quarantined (owner, ticket, five-day fix target); quarantined tests listed but excluded from the pass rate.

- Integration cut-off: no new integration enters staging in the final sprint; "integrated" means failure modes tested.

- Incremental UAT: the client tests each feature when it is done, not all at the end.

- Shared-service rule: a critical defect in a shared service triggers an impact check on every release using it.

- Release criteria agreed with the client at sprint start, so "green" is defined before anyone is under pressure.

Ownership: I raise these at the retrospective and own the flaky-test policy and release criteria; each other change gets a named owner and start sprint. New QAs own a named journey with a buddy from week one.

Metrics for the client:

- Critical-journey readiness: share of agreed critical journeys passing end-to-end on the release candidate, per journey.

- Escaped defects: defects found in UAT or production, by severity and by the stage that should have caught them.

- Open critical defects and quarantined tests: age of open severity 1–2 defects, plus the quarantined-test count.

Not measured: test cases written or executed, raw pass percentage on its own, bugs per tester, or automation percentage as a target. All are easy to game and none shows whether a release is safe.